## Decision Log
Decision ID | Date | Decision Required | Options Considered | Decision Made | Decision Owner | Impact | Status | Notes
D-001 | 2026-01-23 | Confirm governance cadence | Weekly vs bi-weekly project reviews | Weekly project coordination + monthly executive review | Executive Sponsor | Improves delivery visibility and escalation | Approved | Baseline governance cadence
D-002 | 2026-02-13 | Select research methodology | Qualitative only vs quantitative only vs mixed method | Mixed qualitative + quantitative approach | Research Lead | Provides depth and measurable evidence | Approved | Supports program objectives
D-003 | 2026-03-20 | Confirm fieldwork readiness | Proceed vs delay launch | Proceed after final quality checks | Research Lead | Maintains planned timeline | Approved | All critical preparation activities completed
D-004 | 2026-05-08 | Prioritize emerging insight validation | Immediate stakeholder review vs wait for final synthesis | Focused stakeholder review before final synthesis | Commercial Lead | Reduces rework and improves alignment | Approved | Linked to integrated insight development
D-005 | 2026-06-05 | Confirm executive readout format | Detailed research report only vs executive presentation + report | Executive presentation supported by final research report | Commercial Leadership | Improves decision-oriented communication | Pending | Decision required before final reporting

## Action Log
Action ID | Action Description | Owner | Date Raised | Due Date | Priority | Status | Related Workstream | Escalation Required | Notes
A-001 | Confirm final stakeholder review attendees | Project Coordinator | 2026-02-09 | 2026-02-13 | High | Completed | Research Planning | No | Confirmed before design approval
A-002 | Provide weekly recruitment progress update | Research Partner | 2026-03-27 | 2026-04-03 | High | Completed | Data Collection | No | Included in weekly status report
A-003 | Complete additional survey data-quality validation | Data / Analytics | 2026-04-14 | 2026-04-17 | High | In Progress | Data Collection | No | Monitor impact on final sample
A-004 | Prepare integrated qualitative and quantitative insight summary | Research Lead | 2026-05-25 | 2026-06-05 | High | In Progress | Analysis | No | Required before preliminary findings
A-005 | Confirm executive presentation attendees | Project Coordinator | 2026-06-08 | 2026-06-12 | Medium | Not Started | Reporting | No | Schedule after preliminary findings
A-006 | Prepare lessons-learned workshop | Project Coordinator | 2026-07-06 | 2026-07-17 | Low | Not Started | Program Closure | No | To be held before closure

## Instructions
Item | Details
Purpose | Decision and Action Logs for the Global Pharmaceutical Market Research Program.
Decision Log | Use this sheet to document important decisions, ownership, rationale and project impact.
Action Log | Use this sheet to track commitments, owners, due dates, priorities and completion status.
Escalation | Mark Yes when an action requires management attention or cannot be resolved within the agreed timeline.
Portfolio note | This is a fictional portfolio case study; no confidential client or participant information is included.