## Risk Register
Risk ID | Risk Category | Risk Description | Probability | Impact | Risk Score | Risk Level | Owner | Mitigation / Response | Status | Target Date
R-001 | Recruitment | Participant recruitment may take longer than planned, delaying fieldwork. | Medium | High | 6 | High | Research Partner | Monitor recruitment weekly; maintain backup recruitment channels and escalation thresholds. | Open | 2026-04-10
R-002 | Data Quality | Participant or survey response quality may be below required standards. | Medium | High | 6 | High | Data / Analytics | Apply screening criteria, quality checks, validation rules and periodic data reviews. | Open | 2026-04-17
R-003 | Stakeholder | Delayed stakeholder feedback may affect research design or approvals. | Medium | High | 6 | High | Project Coordinator | Agree review timelines, send pre-reads and maintain an escalation path for overdue decisions. | Open | 2026-02-20
R-004 | Scope | Research objectives may change after project initiation. | Medium | High | 6 | High | Research Lead | Use formal change assessment covering scope, timeline, resource and quality impacts. | Open | 2026-02-13
R-005 | Vendor | External research partner may miss agreed deliverables or timelines. | Low | High | 3 | Medium | Project Coordinator | Track vendor milestones, conduct regular reviews and establish escalation procedures. | Open | 2026-03-20
R-006 | Cross-Market | Differences between markets may create inconsistencies in research execution or interpretation. | Medium | Medium | 4 | Medium | Research Lead | Use a common research framework with documented local adaptations and cross-market reviews. | Open | 2026-04-24
R-007 | Timeline | Concurrent workstreams may create resource or schedule conflicts. | Medium | Medium | 4 | Medium | Project Coordinator | Maintain an integrated schedule, dependency tracker and weekly capacity review. | Open | 2026-03-13
R-008 | Compliance | Research activities may require additional compliance or legal review. | Low | High | 3 | Medium | Compliance / Legal | Identify review requirements during planning and build approval time into the schedule. | Open | 2026-02-27
R-009 | Insights | Qualitative and quantitative findings may not initially align. | Low | Medium | 2 | Low | Research Lead | Conduct structured triangulation and investigate differences before finalizing conclusions. | Open | 2026-05-29
R-010 | Technology | Survey or data-collection platform issues may interrupt fieldwork. | Low | Medium | 2 | Low | Data / Analytics | Perform platform readiness checks and maintain contingency procedures for data collection. | Open | 2026-03-20

## Issue Log
Issue ID | Date Identified | Issue Description | Impact | Priority | Owner | Action / Resolution | Status | Target Resolution Date | Notes
I-001 | 2026-03-30 | Recruitment pace is below the planned weekly target in one market. | Potential fieldwork delay | High | Research Partner | Increase recruitment outreach and review progress twice weekly. | Open | 2026-04-10 | Escalate if target remains below threshold.
I-002 | 2026-04-14 | A subset of survey responses requires additional quality validation. | Potential data-quality impact | Medium | Data / Analytics | Run additional validation checks and remove non-compliant responses. | In Progress | 2026-04-17 | Monitor impact on final sample.
I-003 | 2026-05-04 | Stakeholder requested clarification on an emerging research theme. | Potential analysis delay | Medium | Research Lead | Schedule focused review and document agreed interpretation. | Resolved | 2026-05-08 | Closed after stakeholder alignment.

## Risk Summary
Metric | Value
Total Risks | 10
High Risks | 4
Medium Risks | 4
Low Risks | 2
Open Risks | 10
Total Issues | 3
Open Issues | 1
In Progress Issues | 1
Resolved Issues | 1

## Instructions
Item | Details
Purpose | Risk and Issue Register for the Global Pharmaceutical Market Research Program.
Risk Score | Illustrative score based on Probability × Impact using a simple 1–3 scale.
Risk Level | High, Medium or Low based on the illustrative score.
How to use | Update risk status, owners, mitigation actions and dates as project conditions change.
Issue Log | Use the Issue Log for problems that have already occurred and require resolution.
Portfolio note | This is a fictional portfolio case study; no confidential client or participant information is included.