## Project Schedule
Task ID | Workstream | Activity | Owner | Start Date | End Date | Duration (Days) | Status | Dependency | Milestone | Notes
1.1 | Program Initiation | Business Case | Project Coordinator | 2026-01-05 | 2026-01-09 | 5 | Completed |  | Yes | Program authorization
1.2 | Program Initiation | Program Charter | Project Coordinator | 2026-01-08 | 2026-01-16 | 9 | Completed | 1.1 | Yes | Governance approval
1.3 | Program Initiation | Stakeholder Identification | Project Coordinator | 2026-01-12 | 2026-01-16 | 5 | Completed | 1.1 | No | Initial stakeholder map
1.4 | Program Initiation | Governance Setup | Project Coordinator | 2026-01-15 | 2026-01-23 | 9 | Completed | 1.2 | Yes | Governance established
2.1 | Research Planning | Business Question Definition | Research Lead | 2026-01-19 | 2026-01-30 | 12 | Completed | 1.2 | No | Align business questions
2.2 | Research Planning | Research Objectives | Research Lead | 2026-01-26 | 2026-02-06 | 12 | Completed | 2.1 | Yes | Objectives approved
2.3 | Research Planning | Methodology Selection | Research Lead | 2026-02-02 | 2026-02-13 | 12 | Completed | 2.2 | No | Mixed-method approach
2.4 | Research Planning | Research Design Review | Research Lead | 2026-02-09 | 2026-02-20 | 12 | Completed | 2.3 | No | Quality review
2.5 | Research Planning | Stakeholder Approval | Commercial Lead | 2026-02-16 | 2026-02-27 | 12 | Completed | 2.4 | Yes | Research design approved
3.1 | Research Preparation | Discussion Guide Development | Qualitative Lead | 2026-02-23 | 2026-03-06 | 12 | Completed | 2.5 | No | Interview guide
3.2 | Research Preparation | Survey Instrument Development | Quantitative Lead | 2026-02-23 | 2026-03-13 | 19 | Completed | 2.5 | No | Survey instrument
3.3 | Research Preparation | Sample Definition | Research Lead | 2026-03-02 | 2026-03-13 | 12 | Completed | 2.5 | No | Target sample
3.4 | Research Preparation | Fieldwork Readiness Review | Project Coordinator | 2026-03-09 | 2026-03-20 | 12 | Completed | 3.1, 3.2, 3.3 | Yes | Ready for fieldwork
4.1 | Data Collection | Qualitative Recruitment | Research Partner | 2026-03-23 | 2026-04-17 | 26 | Completed | 3.4 | No | Recruit participants
4.2 | Data Collection | Qualitative Interviews | Qualitative Lead | 2026-04-06 | 2026-05-01 | 26 | Completed | 4.1 | No | Interviews
4.3 | Data Collection | Quantitative Survey Launch | Quantitative Lead | 2026-03-23 | 2026-04-24 | 33 | Completed | 3.4 | No | Survey fieldwork
4.4 | Data Collection | Data Quality Monitoring | Data / Analytics | 2026-04-06 | 2026-05-08 | 33 | Completed | 4.2, 4.3 | No | Quality checks
4.5 | Data Collection | Fieldwork Completion | Project Coordinator | 2026-05-04 | 2026-05-08 | 5 | Completed | 4.4 | Yes | Fieldwork complete
5.1 | Analysis | Qualitative Thematic Analysis | Qualitative Lead | 2026-05-11 | 2026-05-22 | 12 | Completed | 4.5 | No | Themes and insights
5.2 | Analysis | Quantitative Data Validation | Data / Analytics | 2026-05-11 | 2026-05-22 | 12 | Completed | 4.5 | No | Validate dataset
5.3 | Analysis | Quantitative Analysis | Data / Analytics | 2026-05-18 | 2026-05-29 | 12 | Completed | 5.2 | No | Analysis
5.4 | Analysis | Integrated Insight Development | Research Lead | 2026-05-25 | 2026-06-05 | 12 | In Progress | 5.1, 5.3 | Yes | Synthesize findings
6.1 | Reporting | Preliminary Findings | Research Lead | 2026-06-08 | 2026-06-12 | 5 | Not Started | 5.4 | Yes | Initial readout
6.2 | Reporting | Stakeholder Validation | Commercial Lead | 2026-06-15 | 2026-06-19 | 5 | Not Started | 6.1 | No | Validate implications
6.3 | Reporting | Final Research Report | Research Lead | 2026-06-22 | 2026-07-03 | 12 | Not Started | 6.2 | Yes | Final research output
6.4 | Reporting | Executive Presentation | Project Coordinator | 2026-07-06 | 2026-07-10 | 5 | Not Started | 6.3 | Yes | Executive readout
7.1 | Program Closure | Lessons Learned | Project Coordinator | 2026-07-13 | 2026-07-17 | 5 | Not Started | 6.4 | No | Capture lessons
7.2 | Program Closure | Knowledge Transfer | Project Coordinator | 2026-07-13 | 2026-07-17 | 5 | Not Started | 6.4 | No | Handover
7.3 | Program Closure | Program Closure | Executive Sponsor | 2026-07-20 | 2026-07-24 | 5 | Not Started | 7.1, 7.2 | Yes | Formal closure

## Milestones
Milestone | Target Date | Status | Related Phase | Notes
Program Charter Approved | 2026-01-16 | Completed | Program Initiation | Governance baseline
Research Design Approved | 2026-02-27 | Completed | Research Planning | Design approved
Fieldwork Ready | 2026-03-20 | Completed | Research Preparation | All instruments ready
Fieldwork Complete | 2026-05-08 | Completed | Data Collection | Data collection complete
Integrated Insights Validated | 2026-06-05 | In Progress | Analysis | Current key milestone
Preliminary Findings Presented | 2026-06-12 | Not Started | Reporting | Initial readout
Final Report Approved | 2026-07-03 | Not Started | Reporting | Final research output
Executive Readout | 2026-07-10 | Not Started | Reporting | Leadership presentation
Program Closure | 2026-07-24 | Not Started | Program Closure | Formal closure

## Instructions
Item | Details
Workbook | Project Schedule
Purpose | Working schedule for the Global Pharmaceutical Market Research Program.
How to use | Update status, dates, owners and notes as project conditions change.
Status values | Not Started ¦ In Progress ¦ Completed ¦ At Risk ¦ Delayed
Date format | DD-MMM-YYYY
Dashboard readiness | The Project Schedule sheet is structured for future Power BI reporting.